Below is a 7-day crash plan that keeps you squarely in the data seat yet produces a demo people can click through.
Anything not essential to a walk-through next week is either simplified or deferred.

## 0. Ruthless Scope Cut — What Stays / Goes
Keep (must-have by Day 7)	Drop or Stub (add later)
• CAMS + Sentinel-3 ingest for one metro area (Berlin) and its 50 km buffer	Anomaly-detection model (flag simple z-score spikes inline instead)
• Daily normalisation + risk-score function	30-day rolling store → keep 7 days only
• Rule-based advice categories (no ML selector)	XGBoost selector & MLflow registry
• Scripted chatbot phrasing templates	Full LLM integration (add after demo)
• Streamlit one-page UI (map optional)	React-Native / mobile polish

This keeps the work to ~25 focused hours.

## 1-Week Countdown
Day	Goal	Concrete Tasks & Tips
Mon	Repo & Data Access	• Scaffold repo • Create .env for API keys • Write tiny script that downloads today + 3-day CAMS forecast (AQI, pollen, temp) for Berlin bbox (use CDS API “subset” request). • Copy one Sentinel-3 UV GeoTIFF from Copernicus demo bucket instead of full GEE export (saves hours).
Tue	Data Harmonisation	• Reproject CAMS grib or netCDF to 0.01° grid with xarray. • Reproject UV raster to same grid. • Save each variable as single COG per day to data/. • Write load_grid(date) helper that returns numpy arrays.
Wed	Risk Score + Advice Rules	• Implement simple min-max scaling per variable. • Hard-code weight table per health condition (e.g. asthma, pollen allergy, sun sensitive). • Build risk_vector(lat, lon, date, profile) → returns dict. • Create 8–10 advice categories + choose_advice(risk_dict, profile) rules.
Thu	Chatbot Script & REST API	• Write Jinja templates: “Because of {{risk}}, I recommend {{advice}}.” • FastAPI with two endpoints: /risk → returns JSON /chat → returns templated sentence. • Unit-test both.
Fri	Streamlit / Quick UI	• One page: – Sidebar: pick health flags + datetime – Center: show risk numbers + coloured bar – “Ask SkyWell” box hits /chat and prints reply. • Optional: add Folium map tile showing risk heat-map (one line folium.raster_layers.ImageOverlay).
Sat	Polish & Fix	• Run end-to-end for Monday-to-Sunday dates. • Add simple in-memory cache (dict) so repeat calls are instant. • Write 1-page README with run commands.
Sun	Deploy & Demo	• Push to GitHub. • Deploy FastAPI + Streamlit on Render.com free tier (one button). • Record 1-minute Loom showing: set profile → get risk → chat reply.

## File/Folder Skeleton
bash
KopierenBearbeiten
skywell/
├── etl/
│ └── fetch.py # Mon
├── data/ # Tue (COGs stored here)
├── core/
│ ├── grid.py # Tue
│ ├── risk.py # Wed
│ └── advice.py # Wed
├── api/
│ └── main.py # Thu
├── ui/
│ └── app.py # Fri
├── tests/ # Thu
└── README.md # Sat

## What You’ll Show Next Week
1. Streamlit page – pick “pollen-allergy + asthma”, click “Get today’s risk”.
2. JSON panel reveals scaled values & colour bars.
3. Press “Ask SkyWell” → scripted chatbot:
  “Because Berlin’s PM2.5 is high (45 µg m⁻³) and grass pollen is very high, I recommend avoiding outdoor exercise until 18:00 and wearing an FFP2 mask.”
4. (Optional) Leaflet mini-map overlaying the UV COG tile.
That satisfies stakeholders, demonstrates data ingestion, processing, and personalised advice—all in one week. Anything deeper (ML selector, 30-day anomalies, full LLM) slides into Phase 2.
##### Du:
Okay now fetch a detailled version for that reduced 7-days plan that also contains the optional steps to re-turn it into the initial 5-sprints-plan
###### ChatGPT:
Thought for 5 seconds
# 7-Day “Crash” MVP Plan
(with plug-ins that let you grow back into the full 5-Sprint roadmap later)

## 📅 Day-by-Day Breakdown
Day	Core Deliverables (finish in 6–8 h)	Optional / “Future-Sprint Hook”<br><sub>(adds 1–3 h, plants code stubs & TODOs so you can re-activate the original 5-sprint scope later)</sub>
Mon ETL Bootstrap	1. etl/fetch.py • CAMS subset query for Berlin bbox (AQI, pollen, temp, 4 × daily forecast steps). • Download single Sentinel-3 UV demo GeoTIFF. 2. .env.example with CDS API key placeholders. 3. GH-Action etl.yml → runs fetch daily at 06:00 UTC and stores raw files under raw/YYYY-MM-DD/.	Stub: write etl/gee_export.py with pass body and a docstring explaining how to swap demo UV for full GEE export (Sprint-1 task).
Tue Grid Harmonisation	1. core/grid.py • Reproject CAMS NetCDF + UV TIFF to 0.01° grid with xarray → 3 numpy arrays. 2. Write each array as COG into data/YYYY-MM-DD_{var}.tif (compress=DEFLATE). 3. Helper load_grid(date) returns dict {var: np.ndarray}.	Hook: add CLI flag --history=N to grid.py that loops past N days – will power 30-day rolling store later.
Wed Risk & Advice Rules	1. core/risk.py • Min-max normalisation tables. • risk_vector(lat, lon, date, profile) returns dict with raw + scaled values & colour codes. 2. core/advice.py • 8–10 rule-based advice categories. • choose_advice(risk, profile) returns category slug + short text. 3. Unit tests in tests/test_risk.py.	Hook: create empty class AdviceSelectorML with fit(X, y) / predict(X) – leave pass; commit so later Sprint-3 can just fill it in.
Thu REST API + Chat Script	1. api/main.py (FastAPI) with routes: /risk → JSON, /chat → templated sentence. 2. chatbot/templates/ Jinja2 templates (“Because of {{pollutant}} …”). 3. Simple in-memory dict cache (4-day TTL) inside api/cache.py.	Hook: add /anomaly route returning "TODO" and create models/anomaly.py skeleton with placeholder detect() – ties to Sprint-2.
Fri Streamlit UI	1. ui/app.py (single page): • Sidebar health checkboxes + date picker (today→+3). • Calls /risk and /chat, displays JSON + coloured bar. • Button “See Map” toggles Folium overlay using UV TIFF. 2. Dockerfile + requirements.txt.	Hook: in ui/app.py leave TODO to load raster tiles directly from COG URL once 30-day history exists (Sprint-1/2 enhancement).
Sat Polish & Tests	1. Run black / ruff; update README install & run steps. 2. Write integration test tests/test_api.py hitting running FastAPI locally. 3. Add make demo script that launches FastAPI & Streamlit together (two processes, or uvicorn + streamlit run).	Hook: env switch SKYWELL_MODE=lite/full – code paths reference it so later you can enable ML selector & anomaly service without refactor.
Sun Deploy & Record Demo	1. Push to GitHub; connect Render.com “Blueprint” → deploy FastAPI container; second web-service for Streamlit (free tier). 2. Set Render cron job (07:00 UTC) to run python etl/fetch.py daily. 3. Record 1-min Loom (or Zoom GIF) showing: select profile → click → see advice.	Hook: in Render YAML add commented block for “worker-30-day-history” (disabled). When you expand to full ETL, just uncomment.

## 📂 Folder Skeleton (already includes hooks)
bash
KopierenBearbeiten
skywell/
├── api/ # FastAPI service
│ ├── main.py
│ └── cache.py
├── chatbot/
│ └── templates/ # Jinja2 text snippets
├── core/
│ ├── grid.py
│ ├── risk.py
│ ├── advice.py
│ └── selector_ml.py # empty class (future Sprint-3)
├── data/ # Tue: COG rasters
├── etl/
│ ├── fetch.py
│ ├── gee_export.py # placeholder
│ └── grid_to_cog.py # helper if split
├── raw/ # Mon: downloaded originals
├── tests/
│ ├── test_risk.py
│ └── test_api.py
├── ui/
│ └── app.py # Streamlit
├── .github/workflows/
│ └── etl.yml
└── README.md

## ✈️ How to Re-Expand into the 5-Sprint Plan
Future Sprint	Activate Hook(s)	Extra Work Needed
Sprint-1 (full ETL)	etl/gee_export.py, grid.py --history 30, enable Render worker	Pull full Sentinel-3 via GEE; write 30-day COGs to skywell-history bucket
Sprint-2 (anomaly)	Fill models/anomaly.py, enable /anomaly route	Use last-30 COGs, write Isolation-Forest or moving-zscore; expose flags
Sprint-3 (ML selector)	Implement selector_ml.py; swap call in advice.py	Train on synthetic / user feedback; persist with joblib
Sprint-4 (LLM)	Replace scripted Jinja in chatbot/templates with dynamic prompt; call OpenAI	Add guardrails; cache completions
Sprint-5 (full UI / mobile)	Expand ui/app.py map, or start React repo	Add auth, prettier map, PWA build

## ⚠️ Risk & Mitigation for 7-Day Push
Risk	Mitigation
API quota / slow downloads	Limit CAMS request to Berlin bbox & two forecast runs per day.
Streamlit + FastAPI CORS issues	Set allowed_origins=["*"] in FastAPI during MVP.
Time over-run on GIS reprojection	Use coarse bilinear resampling and cache the affine transform; accept minor error for demo.

### You are now set to finish an end-to-end demo in one week and still have clean stubs that expand seamlessly into the comprehensive 5-sprint roadmap whenever bandwidth returns.
Ping me on any day for code snippets or debugging help. Good luck — you’ve got this!

Initial 5 sprint / 4-5 weeks plan:
# SkyWell ― Data-First MVP Plan
(focus on data engineering + data science, with an optional thin app at the end)

## 0. Purpose & Scope
You want an MVP that
- excels at data engineering & modelling (remote-sensing ETL, anomaly detection, personalised recommendations),
- keeps all UI/app work lightweight and optional,
- stores only the data required for science (rolling 30 days) while serving today + 3-day forecasts instantly.

## 1. Top-Level Objectives
#	Objective	Key Outputs
1	Solid remote-sensing ETL	Re-usable pipeline ingesting CAMS & Sentinel-3, cleaned & gridded
2	Anomaly-detection service	Flags spatial & temporal outliers in UV, pollen, AQI
3	Personalised risk engine	Builds per-tile feature vector & risk score from base layers + user profile
4	Advice-selector ML model	Predicts which recommendation category suits a user-situation
5	LLM / scripted chatbot layer	Turns category → natural-language advice
6	(Optional) Thin front-end	FastAPI endpoints or Streamlit / React demo that calls the APIs

## 2. Delivery Timeline (5 One-Week Sprints)
### Sprint 0 – Repo & DevOps Warm-up (2–3 days)
- Create monorepo folders: etl/, models/, api/, notebooks/, frontend/
- GitHub Actions: lint + unit tests + nightly ETL run
- Provision:
  - skywell-cache bucket / Redis → keeps today + 3
  - skywell-history bucket → rolling 30-day store
  - Managed PostGIS (or GeoParquet in cloud storage)

### Sprint 1 – Remote-Sensing ETL Core
1. Data wrappers
  1. CAMS forecast API → air-quality, pollen, temperature
  2. Sentinel-3 (OLCI-derived UV) via Google Earth Engine export
2. Grid harmonisation – re-project to 0.01° (~1 km) grid with xarray → write COG files (Cloud-Optimised GeoTIFF) per variable/day into skywell-history.
3. Operational cache – copy today + 3-day layers into Redis (TTL = 4 days) for sub-400 ms API reads.
4. Manifest table – PostGIS table with (date, variable, path, bucket).
Deliverables: etl/ingest.py, nightly GH Action, one week of data stored & validated.

### Sprint 2 – Anomaly Detection Service
1. Temporal anomalies – rolling 30-day z-score or STL residuals per tile×variable (reads only the last 30 COGs).
2. Spatial anomalies – same-day Local Moran I or 8-neighbour z-score for local spikes.
3. API route GET /anomaly?lat=…&lon=…&date=… → returns flags + severity.
Deliverables: models/anomaly.py, api/anomaly_routes.py, notebook visualising recent spikes.

### Sprint 3 – Personal Risk & Advice-Selector ML
1. Risk vector builder – returns normalised indices + anomaly flags for any (lat, lon, date).
2. Synthetic profile generator – thousands of fake users with condition flags (asthma, pollen allergy, etc.) for initial training.
3. Advice taxonomy – 10-15 canonical advice categories (e.g. “Stay indoors 12-15 h”, “Wear SPF 50”).
4. Train selector – XGBoost (multiclass) mapping (risk vector + profile) → advice category. Track Top-1 & Top-3 accuracy.
5. Model registry – save artefacts with MLflow or DVC.
Deliverables: models/recommend_selector.pkl, metrics report, get_advice() helper.

### Sprint 4 – LLM / Chatbot Layer
1. Prompt templates – Jinja strings with slots {profile}, {risk_factors}, {advice}.
2. Generator wrapper –
  1. calls selector → gets category,
  2. renders prompt,
  3. sends to OpenAI (or local Llama) → returns phrased advice.
3. Guardrails – rule filter to avoid unsafe medical claims; fallback to canned text if LLM errors.
4. Unit tests – selector determinism; LLM variability only in wording.
Deliverables: chatbot/generator.py, tests, example conversations.

### Sprint 5 – Thin App / API Gateway (Optional Depth)
Lite track:
- FastAPI only, three endpoints:
  - /risk → reads Redis (today+3)
  - /anomaly → PostGIS & COGs
  - /chat → risk → selector → LLM → response
Full track:
- Streamlit or small React+Leaflet front-end hitting the same API.
- Tailwind styling & anonymous auth if desired.
Deployment: Fly.io, Render, or Cloud Run.

## 3. Storage Strategy
Layer	Tech & TTL	Purpose	Size @ Germany (3 vars)
Operational cache	Redis (4-day TTL)	Instant API responses for today + 3-day forecast	< 10 MB RAM
Analytical store	COG rasters & GeoParquet tables in skywell-history bucket (rolling 30 days)	anomaly windows, trend features, ML training, audit	≈ 220 MB disk
Long-term archive	Nearline / Glacier tar.gz (monthly)	optional future research, reproducibility	~2.6 GB / year

COG = Cloud-Optimised GeoTIFF (for raster layers)
GeoParquet = Parquet with geometry metadata (for per-tile tabular vectors)

## 4. Key Performance Targets
KPI	Target
ETL freshness lag	< 3 h after satellite release
Selector Top-1 accuracy	≥ 70 % on synthetic hold-out
Anomaly precision @30	≥ 0.8
/chat P95 latency (excluding LLM)	< 400 ms
Rolling-store footprint	≤ 300 MB

## 5. Next Steps After MVP
1. Replace synthetic data with user feedback to retrain selector.
2. Fine-tune LLM on domain Q&A logs.
3. Add reinforcement-learning loop to optimise long-term health outcomes.

### Ready to start?
Pick Sprint 1 – ETL and I can supply starter code scaffolds and command-line examples for COG & GeoParquet creation.